## To Customer
DAILY REPORT
PROJECT NAME | Desert HS Modernization |  | DATE |  | 08/22/2022
CONTRACT NO. | 5976 |  | PROJECT ID |  | 5976
TASK ORDER NO. | N/A |  | DOCUMENTED BY |  | Kim, Hyun Myung
CONTRACTOR | LOCATION | MANPOWER |  | TASK
|  | NO. OF SUPER | NO. OF WORKERS
Ace Fence Company | Bldg 400 | 1 | 3 | Fencing installation
5 Star Elevator Service |  | 0 | 0
TOTAL
INSPECTIONS
Name of Inspector | Agency | Location |  | Task |  | Result
Inpsector A | LAISD | 1st Floor Electrical Room |  | Rough Electrical |  | Pass
NOTE
Visitor : Material Delivery