## Daily Report
DAILY REPORT
PROJECT NAME | Sneeze Partition Installation |  |  | DATE | 05/03/2021
CONTRACT NO. | 9055-017.00.01 |  |  | PROJECT ID | 6261
DOCUMENTED BY | Kim, Hyun Myung |  |  | START TIME | 07:00
WEATHER | Sunny |  |  | END TIME | 16:00
CONTRACTOR | TRADE | MANPOWER |  | EQUIPMENT UTILIZATION | WORK PERFORMED
|  | NO. OF WORKERS | HOURS /Day
Exbon Development Inc. | Carpenter | 2 | 4 | Forklift | Sneeze Partition Installation
JPUS | Laborer | 2 | 4 | Dump Truck | Existing Partition Removal
TOTAL |  | 0
TESTS & INSPECTIONS
Inspection is scheduled on May 4, 2021 at 3PM.
CORRECTIONAL ITEMS
New frosted panel has a crack. Needs to be replaced.
NOTE
All punchwork need to be performed during off-hours.